## Sheet1
YMCA 150th Anniversary Campaign Management (Example) | Timeframe | Timeframe | Timeframe | Priority Status | Creation Stage | Lead Team | PARTNERS | FINAL COSTS | STATUS | NOTES | DECISION STATUS
CAMPAIGN PHASE | 2024 | 2025 | 2026
Workforce South Plains -
Hot Workforce - Outreach Services | 2022-09-08 |  |  | Internal Production | Current client | Mel, Joseph, Olivia, Thomas, Janie, Anakin |  |  | Not Yet Started | Brand Management, Design Collateral, Project Support for Special Projects, Social Media, Expanding online presence | Bid
Port San Antonio – 90th Telcom - Engineer & Design an IT Project |  |  |  |  | Don |  |  | 144999.99 | ?
Audience Analysis
Audience Analysis | 1/2 - 1/16 |  |  | High | Not Yet Started | Executive/Project Leadership |  |  | In Progress | Working with YMCA Staff/Project Team upon contract award
Solano County | 2023-03-07 |  |  |  | janie |  |  |  | No Bid | Working with YMCA Staff/Project Team upon contract award
Houston Community College Website Redesign | 2023-03-08 | [7 empty] | CANCELLED | Working with YMCA Staff/Project Team upon contract award
Army Media Reporting & Social Media Software (Sources Sought) | 2023-02-24 |  |  |  | Andrea |  |  |  | Submitted | Working with YMCA Staff/Project Team upon contract award
Texas Historic Sites / Atlas Re-write | 2023-02-27 |  |  |  | Joseph/Angel |  |  |  | No Bid | Working with YMCA Staff/Project Team upon contract award
City of North Platte Website Redesign/Implementation | 2023-03-06 | [7 empty] | No Bid | Working with YMCA Staff/Project Team upon contract award
UT Health San Antonio Monarch Website Updates |  |  |  |  | Joseph/Angel |  |  |  | In Progress | Working with YMCA Staff/Project Team upon contract award
RELLIS Website SOW | 2023-02-23 |  |  |  | Melissa |  |  |  | Submitted | Working with YMCA Staff/Project Team upon contract award
User Interface/User Experience Design Consultant for Harris County Toll Road Authority | 2023-02-20 | [7 empty] | No Bid | Working with YMCA Staff/Project Team upon contract award
Juror Participation Community Outreach Campaign for Harris County | 2023-03-07 |  |  |  | Joseph/Melissa/Janie |  |  |  | Submitted | Working with YMCA Staff/Project Team upon contract award
VIA Website Design & Audit RFP | 2023-04-13 |  |  |  | Joseph | Mel, Joseph, Olivia, Thomas, Janie, Sandra |  |  | In Progress | Working with YMCA Staff/Project Team upon contract award
Texas General Land Office - Website Services | 2023-03-31 |  |  |  |  | Janie, Melissa, Joseph |  |  | Not Yet Started | Working with YMCA Staff/Project Team upon contract award
TPWD RFQ - Volunteer Management System G6 | 2023-03-28 | [7 empty] | Not Yet Started | Working with YMCA Staff/Project Team upon contract award
ILANG Recruiting Advertising Campaign | 2023-03-31 |  |  |  | Andrea / Don | Don, Andrea, Joseph, Janie |  |  | Not Yet Started | Working with YMCA Staff/Project Team upon contract award
City of Alpharetta Georgia / Website Development | 2023-04-13 | [7 empty] | Not Yet Started | Working with YMCA Staff/Project Team upon contract award
WiFi Analytics Tool RFQ# 306-23-0249 | 2023-03-30 | [7 empty] | Not Yet Started | Working with YMCA Staff/Project Team upon contract award
WFSHOT Career Lattices RFQ | 2023-03-17 |  |  |  | Janie, Angel | Janie, Mel |  |  | In Progress | Working with YMCA Staff/Project Team upon contract award
DLD DBITS IT Technical DBITS Tickets | 2023-04-25 | [7 empty] | Not Yet Started | Working with YMCA Staff/Project Team upon contract award
DIR-CPO-TMP-564 / Comprehensive Web Development & Managed Services | 2023-04-27 | [8 empty] | Working with YMCA Staff/Project Team upon contract award
Office of Public Utility Council ( OPUC) | 2023-04-10 | [7 empty] | Not Yet Started | Working with YMCA Staff/Project Team upon contract award
Henry County Schools | 2023-04-17 | [7 empty] | Not Yet Started | Working with YMCA Staff/Project Team upon contract award
Working with YMCA Staff/Project Team upon contract award
Visioning | 1/16 - 1/31 |  |  | High | Not Yet Started | Executive/Project Leadership |  |  | Not Yet Started | Working with YMCA Staff/Project Team upon contract award
SWOT | 2023-01-16 |  |  | High | Not Yet Started | Executive/Project Leadership |  |  | Not Yet Started | Working with YMCA Staff/Project Team upon contract award
User Personas | 2/1 - 2/19 |  |  | High | Not Yet Started | Executive/Project Leadership |  |  | Not Yet Started | Working with YMCA Staff/Project Team upon contract award
Campaign Marketing Plan
Action Plan | 2/20- 3/4 |  |  | High | Not Yet Started | Executive/Project Leadership |  |  |  | Working with YMCA Staff/Project Team upon contract award
Approach | 3/5- 3/18 |  |  | High | Not Yet Started | Executive/Project Leadership |  |  |  | Working with YMCA Staff/Project Team upon contract award
Tactics | 4/1-4/18
Branding
Logo | 3/25-4/15 |  |  | High | Not Yet Started | Executive/Project Leadership |  |  |  | Working with YMCA Staff/Project Team upon contract award
Visual Design Elements | 4/15-5/15
Templates | 2023-05-18
Style Guide | 5/20-5/31
Multichannel Integration
150th Celebration Webpage (Initial launch to announce 150th Celebration) | 2024-09-01 |  |  | High | Not Yet Started | Executive/Project Leadership |  |  |  | Working with YMCA Staff/Project Team upon contract award
Social Media | 2024-10-01 |  |  | High | Not Yet Started | Executive/Project Leadership |  |  |  | Working with YMCA Staff/Project Team upon contract award
Video | 2024-11-01
Email Marketing | 2024-11-15
Advertising Plan | 2024-11-15
ADVERTISING/MARKETING/MEDIA ({Merchandise Promotion) | [8 empty] | Not Yet Started
META - FB/IG |  | 2025-06-01 | 2026-06-01 | Medim | Not Yet Started | Project Leadership/Media Team |  |  | Not Yet Started | Working with YMCA Staff/Project Team/Merch Promotion
Email Marketing |  | 2025-06-01 | 2026-06-01 | Medim | Not Yet Started | Project Leadership/Media Team |  |  | In Progress | Working with YMCA Staff/Project Team/Merch Promotion
Geo-Display |  | 2025-06-01 | 2026-06-01 | Medim | Not Yet Started | Project Leadership/Media Team |  |  |  | Working with YMCA Staff/Project Team/Merch Promotion
Organic Social Media (FB,IG,TW,LI) | 2024-10-01 | 2026-01-01 | 2026-06-01 | Medium | Not Yet Started | Project Leadership/Media Team |  |  |  | Working with YMCA Staff/Project Team/Merch Promotion
Social Media Influencers | 2024-10-01 | 2026-01-01 | 2026-06-01 | Medium | Not Yet Started | Project Leadership/Media Team |  |  |  | Working with YMCA Staff/Project Team/Merch Promotion
YouTube Skippable & Unskippable |  | 2025-06-01 | 2026-06-01 | Medim | Not Yet Started | Project Leadership/Media Team |  |  |  | Working with YMCA Staff/Project Team /Merch Promotion
Medical CDID Solicitation #W9124J22R0004 | 2022-05-18 |  |  |  | Don/Andrea | Project Leadership/Media Team |  | 200000 | Completed
UT Correll | 2022-03-16 |  |  |  | WH | Project Leadership/Media Team |  |  | Completed | Drupal Websites - Rebuilds x 4 Heavy Programming
SARA |  |  |  |  | Janie/Melissa | Project Leadership/Media Team
Crosswind PR New work - OurBarndominiumLife |  |  |  |  | Melissa | Project Leadership/Media Team
TDCJ Mobile | [5 empty] | Project Leadership/Media Team |  | 170000 | Submitted
VIA | 2022-06-20 |  |  |  | Joseph | Project Leadership/Media Team
Montgomery County PA | 2022-08-12 |  |  |  |  | Project Leadership/Media Team |  | 173168.87 |  | Graphic Design Services/175k / 5 years
Maryland Army National Guard | 2022-08-01 |  |  |  |  | Project Leadership/Media Team |  |  |  | Mass Adv and Marketing
Harris Voting Outreach | 2022-08-29 |  |  | Internal Production | Bonfire/Joseph | Project Leadership/Media Team | TalkStrategy, Holdsworth |  | Not Yet Started |  | Bid
Performance Tracking & Optimization |  | 2025-06-01 | 2026-06-01 | Medium | Not Yet Started | Project Leadership/Media Team |  |  |  | Working with YMCA Staff/Project Team/Merch Promotion
ADVERTISING/MARKETING/MEDIA (Affluent Donor Driver Plan)
iHeart Podcast |  | 2026-01-01 | 6/31/26 | Medim | Not Yet Started | Project Leadership/Media Team |  | 353725.28 |  | Working with YMCA Staff/Project Team/Affluent Donor Driver Plan
Targeted Email |  | 2026-01-01 | 6/31/26 | Medim | Not Yet Started | Project Leadership/Media Team |  | 22516.4 |  | Working with YMCA Staff/Project Team/Affluent Donor Driver Plan
YouTube Skippable & Unskippable |  | 2026-01-01 | 6/31/26 | Medim | Not Yet Started | Project Leadership/Media Team |  | 138154.8 |  | Working with YMCA Staff/Project Team/Affluent Donor Driver Plan
Organic Social Media (FB,IG,TW,LI) |  | 2026-01-01 | 6/31/26 | Medium | Not Yet Started | Project Leadership/Media Team |  |  |  | Working with YMCA Staff/Project Team/Affluent Donor Driver Plan
Social Media Influencers | 2024-10-01 | 2023-01-01 |  | Medium | Not Yet Started | Project Leadership/Media Team |  |  |  | Working with YMCA Staff/Project Team/Affluent Donor Driver Plan
Community Wide Events (targeted venues) |  |  |  | Medium | Not Yet Started | Project Leadership/Media Team |  |  |  | Working with YMCA Staff/Project Team/Affluent Donor Driver Plan
iHeart OTT |  | 2026-01-01 | 6/31/26 | Medim | Not Yet Started | Project Leadership/Media Team |  |  |  | Working with YMCA Staff/Project Team/Affluent Donor Driver Plan
Performance Tracking & Optimization |  | 2026-01-01 | 6/31/26 | Medium | Not Yet Started | Project Leadership/Media Team |  |  |  | Working with YMCA Staff/Project Team/Affluent Donor Driver Plan
ADVERTISING/MARKETING/MEDIA (150TH Celebration Event Promotion)
META - FB/IG |  |  | 3/1/26 - 6/31/26 | High | Not Yet Started | Project Leadership/Media Team |  |  |  | Working with YMCA Staff/Project Team/150th Event Celebration
Targeted Email |  |  | 3/1/26 - 6/31/26 | High | Not Yet Started | Project Leadership/Media Team |  |  |  | Working with YMCA Staff/Project Team/150th Event Celebration
Geo-Display |  |  | 3/1/26 - 6/31/26 | High | Not Yet Started | Project Leadership/Media Team |  |  |  | Working with YMCA Staff/Project Team/150th Event Celebration
Broadcast (Radio) |  |  | 3/1/26 - 6/31/26 | High | Not Yet Started | Project Leadership/Media Team |  |  |  | Working with YMCA Staff/Project Team/150th Event Celebration
Headline Event & (targeted venues) |  |  | 3/1/26-6/31/26 | High | Not Yet Started | Project Leadership/Media Team |  |  |  | Working with YMCA Staff/Project Team/150th Event Celebration
150th Celebration Webpage |  | 2024-08-01 | 6/31/2026
Social Media Influencers |  |  | 3/1/26 - 6/31/26 | High | Not Yet Started | Project Leadership/Media Team |  |  |  | Working with YMCA Staff/Project Team/150th Event Celebration
Performance Tracking & Optimization |  |  | 3/1/26 - 6/31/26 | Medium | Not Yet Started | Project Leadership/Media Team |  |  |  | Working with YMCA Staff/Project Team/150th Event Celebration
PUBLIC RELATIONS PHASES | [7 empty] | 155000
Strategic Partnerships/Community Groups | 2024-07-01 |  | 2026-06-01 | Medium | Not Yet Started | PR/Events Team |  | 165702.4 | Submitted / LOST | Working with elected officials-County,Municipal,YMCA Leadership
News Releases,Op-Ed Pieces,Media Tours/News Conferences/Tracking News | 2024-08-01 |  | 2026-06-01 | Medium | Not Yet Started | PR/Events Team |  |  |  | Placing Ads,Providing Support for the interview on TV, Radio,Print
Messagng Development/Story Pitching-Placement | 2025-01-01 |  | 2026-06-01 | Medium | Not Yet Started | PR/Events Team |  | 570272.07 | Submitted / LOST | Assisting YMCA Staff with Outreach Topics for Education
EVENT PLANNING PHASES | [7 empty] | 115200 | Submitted / In Review
UT Health Houstion Symposium App | 2023-02-03 |  |  |  | Joseph/Janie |  |  | 75000 | Submitted | App Development
Strategic Planning for Engaging, Interactive 150th Anniversary Events | 2024-05-01 |  |  | High | Not Yet Started | PR/Events Team |  | 129846 | Submitted | English & Spanish representatives in residential & business areas
Define Objective and Scope | 2024-05-01 |  |  | High | Not Yet Started | PR/Events Team |  | 763161.31 | Submitted / LOST | For various public events
Research Analysis | 2024-05-21 |  |  | High | Not Yet Started | PR/Events Team |  | 99590.4 | Submitted /LOST | Maintained by our EventOutreach Manager / Team
Resource Assessment | 2024-06-01 |  |  | High | Not Yet Started | PR/Events Team |  |  | Submitted | The plan will be used for various phases,programs,initiatives
Brainstorm & Conceptualize Events | 2024-06-15 |  |  | High | Not Yet Started | PR/Events Team |  | 4350 | Submitted | These will be used for English and Spanish speaking audiences
Create an Event Calendar | 2024-07-01 |  |  | High | Not Yet Started | PR/Events Team |  | 75000 | Submitted / LOST | These will be in English & Spanish
Marketing & Promotion Strategy | 2024-08-01 |  |  | High | Not Yet Started | PR/Events Team |  | 20520.26 | Submitted / Awarded | Conducted by Event Planning team in English & Spanish
YMCA 150th Events |  | 2025-06-01 | 6/31/2026 | High | Not Yet Started | PR/Events Team |  | 48472 | Submitted / Pending | In all precincts,districts, frequency of events will be approved by YMCA Staff
[8 empty] | 12600 | Submitted
[8 empty] | 63000 | Submittted /Pending
Data Insights |  | 2025-06-01 | 6/31/2026 | Medium | Not Yet Started | PR/Events Team |  |  |  | YMCA Staff
VIDEO PRODUCTION PHASES
Historical Research (Promo Video) | 2024-07-01 |  |  | Medium | Not Yet Started | Video Production Team |  |  |  | Working with YMCA Staff/Project Team/Video Production Crew
Content Strategy | 2024-07-01 |  |  | Medium | Not Yet Started | Video Production Team |  |  |  | Working with YMCA Staff/Project Team/Video Production Crew
Storyboarding & Scripting | 2024-07-20 |  |  | Medium | Not Yet Started | Video Production Team |  |  |  | Working with YMCA Staff/Project Team/Video Production Crew
Location Scouting/Permission | 2024-07-20 |  |  | Medium | Not Yet Started | Video Production Team |  |  |  | Working with YMCA Staff/Project Team/Video Production Crew
Filming (Promo Video) | 2024-09-01 |  |  | Medium | Not Yet Started | Video Production Team |  |  |  | Working with YMCA Staff/Project Team/Video Production Crew
Voiceover/ Music Selection | 2024-09-15 |  |  | Medium | Not Yet Started | Video Production Team |  |  |  | Working with YMCA Staff/Project Team/Video Production Crew
Editing / Post Production | 2024-10-15 |  |  | Medium | Not Yet Started | Video Production Team |  |  |  | Working with YMCA Staff/Project Team/Video Production Crew
Feedback | 2024-10-20 |  |  | Medium | Not Yet Started | Video Production Team |  |  |  | Working with YMCA Staff/Project Team/Video Production Crew
Distribution / Promotion (Video Vignetes) |  | 2025-01-02 | 6/31/2026 | Medium | Not Yet Started | Video Production Team |  |  |  | Working with YMCA Staff/Project Team/Video Production Crew
ACCOUNT MANAGEMENT & REPORTING
Texas Higher Education Board | [9 empty] | Data and Dissemination Portal
Tarrant County | 2022-03-10 | [7 empty] | No Bid | Not Feeling this one - Full Website Redesign
Crosswind UT | 2022-02-28 | [7 empty] | Completed | On going Maintnenace
Office of Consumer Credit Commissionar | 2022-03-14 | [7 empty] | In Progress | Drupal Update
WSA Security Operations Center #2022-011 | 2022-05-19 |  |  |  | WH |  |  | 105000
WSA IT Cloud Services | 2022-05-24
UT Health | 2022-08-09 | [8 empty] | Digital Asset Management Cyber
City of South Lake | 2022-08-19 | [8 empty] | Website Redesign/budget 15k
Tx Dept of Family & Protective Services | 2022-08-10 | [8 empty] | Awareness, Marketing, Communication Services - TalkStrategy?
TWC | 2022-08-09 | [8 empty] | Website Redesign
Willamson County | 2022-08-16 | [8 empty] | Branding/Website/Hosting - 5 years/5 websites
Monthly Meetings with YMCA Staff | Upon Contract Award |  |  | High | Not Yet Started | Project Leadership/Executive Team |  |  |  | Scheduled after the Contract is awarded
Maintaining Internal Procedures to ensure budget control, prompt billing, quality control | 2024-01-02 |  | 6/31/2026 | High | Not Yet Started | Project Leadership/Executive Team |  |  |  | Communicated by the Project Team to YMCA Staff
Analytical Data Reports | Monthly | Monthy | Monthly | High | Not Yet Started | Project Leadership/Executive Team |  |  |  | Provided Monthly and meeting scheduled to discuss
Cost schedules,project sheets for authorized advertising/pre-production estimates | Monthly | Monthly | Monthly | High | Not Yet Started | Project Leadership/Executive Team |  |  |  | Provided Monthly and meeting scheduled to discuss
Status Reports as agreed upon with YMCA Staff | Monthly | Monthly | Monthly | High | Not Yet Started | Project Leadership/Executive Team |  |  |  | Provided Monthly and meeting scheduled to discuss
EVALUATION PLAN
Post Implementation |  | 2025-12-31 | 6/31/2026 | High | Not Yet Started | Project Leadership/Executive Team |  |  |  | Provided Annually and meeting scheduled to discuss